PHASE 3

Material Tracking

Implementation Guide for Field Ops  —  Informed by Krane & Market Research

# 1. Market Research Summary

### Krane (krane.tech)  —  AI-Powered Supply Chain

Krane is a Stanford GSB-founded startup ($9M raised) focused specifically on construction material management. Their platform offers:

- AI-powered supply chain optimization with 95% delivery accuracy claims

- Delivery Module: real-time tracking, delay flagging, and last-mile coordination

- AutoLog Agent: AI that scans spec sets and generates submittal/procurement logs

- LeadTime Agent: predicts procurement delays by modeling alternative scenarios

- KAI Agent ecosystem for automated material intelligence

- Integrations with Procore, Autodesk, CMiC, Primavera P6, and Trimble Viewpoint

### Raken Material Tracking

Raken offers a simpler approach: basic material delivery logging, consumption tracking, and inventory management integrated into their daily reporting flow.

### Our Differentiated Approach

We take a middle path: more intelligent than Raken (AI-powered variance detection, cost code integration) but more practical than Krane (no separate supply chain platform needed). Every material delivery and consumption event feeds directly into our productivity engine and legal documentation layer.

|  | Competitive Positioning Krane is a standalone supply chain tool. Raken treats materials as a reporting feature. Field Ops makes material tracking a first-class citizen that connects to cost codes, productivity analytics, and legal dispute documentation. |
| --- | --- |

# 2. Data Models

### MaterialDelivery Interface

export type DeliveryStatus = 'scheduled' | 'in_transit' | 'delivered' | 'partial' | 'rejected' | 'returned';

export interface MaterialDelivery {

id: string;

projectId: string;

dailyLogId?: string;

date: string;

deliveryTime?: string;

supplier: string;

poNumber?: string;

ticketNumber?: string;

material: string;

csiDivision?: string;

costCodeId?: string;

// Quantities

orderedQuantity: number;

deliveredQuantity: number;

unitOfMeasure: string;

// Verification

receivedBy: string;

status: DeliveryStatus;

condition: 'good' | 'damaged' | 'partial_damage';

damageNotes?: string;

photos?: string[];

// Location

taktZone?: string;

storageLocation?: string;

// Cost tracking

unitCost?: number;

totalCost?: number;

// Lead time tracking

orderDate?: string;

expectedDeliveryDate?: string;

leadTimeDays?: number;

wasLate: boolean;

delayDays?: number;

// Legal linkage

relatedDelayEventId?: string;

backchargeRequired?: boolean;

createdAt: string;

updatedAt: string;

}

### MaterialInventory & Consumption

export interface MaterialInventory {

id: string;

projectId: string;

material: string;

csiDivision?: string;

costCodeId?: string;

currentQuantity: number;

unitOfMeasure: string;

minimumThreshold: number;        // alert when below

reorderPoint?: number;

storageLocation?: string;

lastDeliveryDate?: string;

lastConsumptionDate?: string;

totalDelivered: number;

totalConsumed: number;

totalWasted: number;

wastePercentage: number;         // computed

updatedAt: string;

}

export interface MaterialConsumption {

id: string;

projectId: string;

dailyLogId?: string;

date: string;

inventoryId: string;

material: string;

quantityUsed: number;

unitOfMeasure: string;

costCodeId?: string;

taktZone?: string;

activity?: string;

wasRework: boolean;

wasteQuantity?: number;

notes?: string;

createdAt: string;

}

# 3. UI Components

### Materials Dashboard  —  /materials

Four-tab interface: Deliveries, Inventory, Consumption, and Alerts.

Deliveries Tab: Log incoming deliveries with photo proof, ticket numbers, and quantity verification. Flag discrepancies between ordered and delivered quantities. Auto-link to cost codes. Late delivery alert triggers optional delay event creation.

Inventory Tab: Real-time inventory levels by material. Color-coded threshold indicators (green = good, amber = low, red = below minimum). Waste percentage tracking. Projected depletion dates based on consumption rate.

Consumption Tab: Daily consumption logging linked to work performed entries. Waste tracking by trade and zone. Rework material flagging. Material cost per unit of installed work (feeds productivity engine).

Alerts Tab: AI-flagged anomalies: unusually high consumption rates, waste spikes, delivery delays impacting schedule, materials below reorder point.

### Daily Log Integration

Add a new Materials screen to the daily log (screen 13) that allows quick delivery logging during the daily walkthrough. This creates the bridge between field observation and formal material tracking.

# 4. AI-Powered Features

### Variance Detection

Using the existing Claude AI integration, analyze material consumption patterns and flag anomalies:

- Consumption rate vs. budgeted rate (from cost codes) — flag when 15%+ over

- Waste percentage trending upward — investigate by trade/zone

- Delivery delays impacting critical path — auto-suggest delay event creation

- Material cost escalation — compare delivery costs to bid estimates

### Lead Time Intelligence

Track historical lead times by supplier and material type. Build a predictive model for future orders:

- Average lead time by supplier (updated with each delivery)

- Seasonal variance factors (concrete delivery in winter vs. summer)

- Early warning when a scheduled delivery's lead time exceeds historical average

# 5. Cowork Session Plan

### Session 1: Data Layer (Est. 45 min)

- Add MaterialDelivery, MaterialInventory, MaterialConsumption types

- Add database tables with indexes for project + material + date queries

- Create helper functions for delivery logging, inventory updates, and consumption tracking

- Build auto-inventory-update: when delivery logged, add to inventory; when consumption logged, subtract

### Session 2: Delivery Logging UI (Est. 60 min)

- Create /materials/page.tsx with tabbed layout

- Build DeliveryForm component with photo capture, supplier picker, quantity verification

- Build DeliveryCard component with status badges and discrepancy flags

- Add to daily log as Screen 13 (MaterialsScreen.tsx)

### Session 3: Inventory & Consumption (Est. 60 min)

- Build InventoryGrid component with threshold color coding

- Build ConsumptionForm linked to work performed entries

- Implement waste tracking calculations

- Wire consumption to productivity engine (material cost per unit installed)

### Session 4: AI Alerts & Analytics (Est. 45 min)

- Add /api/materials/analyze route using Claude AI for variance detection

- Build AlertsPanel component showing AI-flagged anomalies

- Add lead time tracking calculations to delivery save flow

- Connect material delays to the delay event and notice log systems

# 6. New Files Manifest

| File Path | Purpose |
| --- | --- |
| src/app/materials/page.tsx | Materials dashboard (deliveries, inventory, consumption, alerts) |
| src/app/api/materials/analyze/route.ts | AI-powered material variance analysis |
| src/components/materials/DeliveryForm.tsx | Delivery logging with photo + quantities |
| src/components/materials/InventoryGrid.tsx | Real-time inventory levels with thresholds |
| src/components/materials/ConsumptionForm.tsx | Daily consumption entry linked to work |
| src/components/materials/AlertsPanel.tsx | AI-flagged anomalies and warnings |
| src/components/daily-log/MaterialsScreen.tsx | Daily log Screen 13: quick delivery entry |
| src/lib/material-analytics.ts | Lead time tracking, waste calcs, threshold alerts |